## Overview
8000 - EXL/F&A Reports automation 2 (Advisory-17 Reports)
KPMG Proposed Start Date: | TBD
KPMG Defined Deadline: | TBD
Calculated Complexity: | Complex
SLA Duration: | TBD
Calculated End Date: | TBD
Scope of Services: | Develop, Test, Debug, Fix, Deploy
Dependencies: | Business Shared Drive, Sharepoint, Microsoft Excel, Outlook, HANA
Comments/Notes:

## Complexity Summary
S.No. | Use Case Attribute | Value | Story Points |  | Legends | Input Needed
1 | Objects - Total Screens/UI | No Objects | 0 |  |  | Computed Value
2 | Business/Validation - Decisions/Rules | 1 to 12 | 1
3 | Interface DB - DB Queries | Query Weightage 1 to 15 | 1
4 | Process Design - Total Process Steps | 51 to 60 | 6
5 | File Process - Excel sheets | 1 to 6 Excel Sheets | 1
6 | File Process - Word/Pdf/Power Point | Handling Structured/Semi-Structured/Unstructured Data | 3
7 | Reports Creation/updation - Bot Execution Report/Metrics Report | NA | 0
8 | Exception Handling (Business/System) | 1 to 10 Exceptions | 1
9 | Target Application UI access mode | Direct Access | 0
10 | Automation Scripting - No. of Scripts need to be build | Up to 6 | 1
11 | Reusable Modules | No Reusable Module | 0
12 | API Interfaces - No of Interface in user story | No API Interfaces | 0
13 | Understanding existing automation (atmx) E2E (Enh. only) | No atmx file | 0
14 | Understanding existing Macro/Other Scripts E2E (Enh. only) | No Macro/Other Scripts | 0
15 | Environment Readiness for Dev/QA/Prod | Environment Readiness for Dev/QA/Prod | 1
16 | Solution Design (SDD) | Multi Bot Architecture without interaction with each other | 2 | .
17 | Test Case Document & QAT | Test Case up to 20 | 1
|  | Total Story Points | 18
|  | Use Case Complexity | Medium
| T-Shirt Size Build Services | Multiplier | Story Points
| Simple | 1 | 15
| Medium | 2 | 30
| Complex | 4 | 60

## TaskList
Process Description | Task Description | Sub Tasks | Comments | Objects - Total Screens/UI | Business/Validation - Decisions/Rules | Interface DB - DB Queries | Process Design - Total Process Steps | File Process - Excel sheets | File Process - Word/Pdf/Power Point | Reports Creation/updation - report Execution Report/Metrics Report | Exception Handling (Business/System) | Target Application UI access mode | Automation Scripting - No. of Scripts need to be build | Reusable Modules needed | API Interfaces - No of Interface in user story
Refresh Engagement Dashboard.
Updating Engagment Summary Dashboard – Recievable Report | Get Input Recievable detail File | 1.Check for Network drive access: \\Usmdcflex009\KSD\department\BET Technology Network Drive. 2.if no access send an exception email. |  |  | 1 |  | 3
|  | 1.Check Recievable detail File from-\\Usmdcflex009\KSD\department\BET Technology Network Drive 2.If zip file (Receivables Report_ YYYY-MM-DD.zip) file not found send exception 3.If file found copy and Paste that zip file in Local folder. |  |  | 1 |  | 3
| Copy master Template to Inprogress folder | 1.Unzip the folder and Open Recievable detail file. |  |  |  |  | 10 | 1
1.Copy Engagement Summary master Template from templates Folder to Inprogress Folder 2.Open Master template file and switch to recievable report sheet. 3.Check if headers are same for both template and Recievable detail File. 4.If not matching,Reorder or rename columns in the Receivable Detail file based on template structure. 5.Add new colums from Receivable file if not present in Template file. 6.Save and close FIle. 7.Connect to recievable report file as database. 8.Copy data whose Engagement Function is Tax only.
| Excel Manipulation | 1.Add a new column with name Invoice Aging days in File. 2.This column will calculate the difference between Bill Clearing date and Billing Date. 3. Convert the difference into days and paste the data in Master template file. 4.Add a new coulmn with name Average Invoice Aging Days. 5.Calculate the average out of Invoice Aging Days by Clinet Name. 6.Go to Column B and convert data to Number. 7.Go to Column H and remove duplicates. 8.Go to Coulmn Q and sort data from largest to smallest. 9.Save File. |  |  |  |  | 2 | 1
Update Engagement Summary Dashboard – Open Engagement | Get Input Engagement Summary File. | 1.Check Engagement summary File from-\\Usmdcflex009\KSD\department\BET Technology Network Drive 2.If file not found send exception 3.If file found copy and Paste that zip file in sub folder |  |  |  |  | 3
| Excel Manipulation | 1.Unzip the file and Connect to Engagement Summary file as Database. 2.Copy data whose Current Engagement Profit Center : Function Desc is Tax group only. |  |  |  |  | 2
| Macro-Updating data from Engagement Summary File to Master Template File. | 1.Open Engagement Summary Master Template File. 2.Switch to Engagement Summary Sheet in Master Template. 3.paste Copied data fromRae report of engagement summary to Engagement Summary sheet in Master Template. 4.Select Column C and convert it to a Number. 5.Select Column D and remove duplicates. 6.Select Column D and convert data into Number. 7.Go to Column G and paste Special by divide. 8.Go to Column Z and Select percentage to dispaly data in correct format. 9.Go to column A1 and upfdate todays date as last refresh date. 10.Save the file. |  |  |  |  | 13
Macro-Updating Engagement numbers in Engagement Summary report sheet. | Updating Engagement numbers in Engagement Summary report sheet for getting remaining fields updated.. | 1 copies all values from Open Engagements!D5:D(last row). 2.and pastes them into Engagement Summary Report!H7 downward, 3.reads all Engagement IDs from “Open Engagements” (column D, row 5 down). 4. compares them to the existing IDs in “Engagement Summary Report” (column H, row 6 down). 5.adds only the new ones to column H with a note in column B—while skipping blanks, skipping duplicates. 6.Save the file. |  |  |  |  | 6
Updating Engagement numbers in Closeout Pivot sheet. | Updating Engagement numbers in Closeout Pivot sheet for getting Code change and notes fields updated. | 1.Values will be uodated for them whose status is showing as closed. |  |  |  |  | 1
Billing and Cash Drive Sheet | Updating partner wise data from Recievables report sheet and engagement summary sheet in the Billing and cash drive sheet. | 1.Copy all Partner names which will be taken form Recievable report. 2.Remove duplicate names from Partners. 3. paste those partner names to Billing and cash drive Sheets. 4.Apply formulas for remaining cloumn to get unbilled total, cash total etc. 5.At the end of the sheet apply formulas to all the cloumns to find total. 6.Repeat this for other two sheets. |  |  |  |  | 6 | 4
Updating all three sheets of data to Sharepoint |  | 1.Create three new workbooks for Engagement summaey Dashboard , Billing and cash drive and Recievables report. 2.Copy data from each sheet and paste it in workbooks. 3.Update all three excel workbooks to Sharepoint.
Extracting details from Engagement letters
Extracting details from Engagement letters and SAN Free range from Mail attachment. | Download engagement report files from sharepoint. | 1.Validate sharepoint link check for access and files. 2.If no Accessand no files send exception to Business. 3.loop through each row and Check if flag Open, then download the engagement letter and email atatchment. 4.Change the Flag to InProgress. |  |  | 1 |  | 4
| Extract fee details from Engagement letters | 1.Copy all Engagement letters and Email Attachments from downloads to Local folder. 2.Loop Through each file of pdf Attachment. 3.Send Engagement letter to LLM and extract the required details from prompts. 4.Also give prompts to what fields to be extracted with keywords. 5.Update the extracted fields from engagement letters to template file. 6.Save the file. |  |  |  |  | 6
| Extract SAN FEE Range from email Attachments | 1.Download Email attachment from Sharepoint list. 2.Get the file name(Engagement Number). 3.Open each atatchment and extaract body from email attachment to a string. 4.Extract required SAN FEE RANGE from the string. 5.Open Template file and update details of the extracted san fee range with the Engagement Number. 6.Close the outlook Attachment. 7.Change the flag to complete in Sharepoint. |  |  |  |  | 7
Upload file in Sharepoint.

## Extension_Config (hidden)
Original Name | Replacement Value
ä | a
A.B. | AB
A/B | AB
Aktiebolag | AB
Company | Co.
Corporation | Corp
Gesellschaft mit beschränkter Haftung | Gmbh
Gmbh & Co | Gmbh
Incorporated | Inc.
Kommanditgesellschaft | KG
ltd | Limited
LTD | Limited
Ltd | Limited
Ltd. | Limited
LTD. | Limited
L.L.C | LLC
Limited Liability Corp | LLC
Limited Liability Corp | LLC
Limited Liability Corporation | LLC
Limited Liability Corporation | LLC
L.P. | LP
Limited Partner | LP
Limited Partnership | LP
Public Limited Co. | PLC
Public Limited Company | PLC
Sà rl | SARL
S.a r.l. | SARL
S.à r.l. | SARL
S.a.r.l. | SARL
Société à responsabilité limitée | SARL
Sociedades por Acciones Simplificada | SAS
Sociedad de responsabilidad limitada | SpA
s.r.o. | sro
spol. s r.o. | sro
društvo s ograničenom odgovornošću | doo

## Assumptions
S.No | Assumption | remarks
1
2

## Queries
S.No | Queries
1

## Rules
Rules to Define Automation Complexity
S. No. | Use Case Attribute | Attribute Weightage | Parameters | Parameter Weightage | Note
1 | Objects - Total Screens/UI | 0.053 | No Objects | 0 | Every 8 total screening/UI, 1 story point to be added
|  |  | 1 to 8 | 1
|  |  | 9 to 16 | 2
|  |  | 17 to 24 | 3
|  |  | 25 to 32 | 4
2 | Business/Validation - Decisions/Rules | 0.053 | No Rules | 0 | Every 12 Business/Validation - Decisions/Rules, 1 story point to be added
|  |  | 1 to 12 | 1
|  |  | 13 to 24 | 2
|  |  | 25 to 36 | 3
|  |  | 37 to 48 | 4
3 | Interface DB - DB Queries |  | No Queries | 0 | Every 15 Query Weightage, 1 story point to be added | Weightage of the Query | Query Description | No of queries | Total Weightage
|  |  | Query Weightage 1 to 15 | 1 |  | 1 | Queries using 1 to 3 tables | 5 | 5
|  |  | Query Weightage 16 to 30 | 2 |  | 2 | Queries using 4 to 8 tables | 1 | 2
|  |  | Query Weightage 31 to 45 | 3 |  | 3 | Queries using more than 8 tables | 1 | 3
|  |  | Query Weightage more than 45 | 4 |  |  |  |  | 10
4 | Process Design - Total Process Steps |  | NA | 0 | Every 10 Process Design - Total Process Steps, 1 story point to be added
|  |  | 1 to 10 | 1
|  |  | 11 to 20 | 2
|  |  | 21 to 30 | 3
|  |  | 31 to 40 | 4
|  |  | 41 to 50 | 5
|  |  | 51 to 60 | 6
|  |  | 61 to 70 | 7
|  |  | 71 to 80 | 8
5 | Applications Involved - No. of Systems | 0.053 | NA | 0 | Removed
|  |  | 1 to 6 | 1
|  |  | 7 to 10 | 2
|  |  | 11 to 15 | 4
6 | File Process - Excel sheets | 0.077 | NA | 0 | Every 6 File Process - Excel sheets, 1 story point to be added
|  |  | 1 to 6 Excel Sheets | 1
|  |  | 7 to 12 Excel Sheets | 2
|  |  | 13 to 18 Excel Sheets | 3
|  |  | 19 to 24 Excel Sheets | 4
7 | File Process - Word/Pdf/Power Point | 0.077 | NA | 0 | Structured Data: 1. Simple fixed field/location/editable text(Ex: Invoice number, date etc.) 2. No Images Semi-Structured Data: 1. Handling clear Images(Ex:Signatures,stamp etc.) 2. Identify free editable text Structured/Semi-Structured/Unstructured Data: 1. Working on Unstructured Data/Form elements 2. Working on Power point file[Copy data from word to PPT vice versa]
|  |  | Handling Structured Data | 1
|  |  | Handling Semi-Structured Data | 2
|  |  | Handling Structured/Semi-Structured/Unstructured Data | 3
8 | Reports Creation/updation - Bot Execution Report/Metrics Report | 0.077 | NA | 0 | Every 2 Reports Creation/updation - Bot Execution Report/Metrics Report, 1 story point to be added
|  |  | 1 to 2 Reports | 1
|  |  | 3 to 4 Reports | 2
|  |  | 5 to 6 Reports | 3
|  |  | 7 to 8 Reports | 4
9 | Exception Handling (Business/System) |  | NA | 0 | Every 10 Exception Handling (Business/System), 1 story point to be added
|  |  | 1 to 10 Exceptions | 1
|  |  | 11 to 20 Exceptions | 2
|  |  | 21 to 30 Exceptions | 3
|  |  | 31 to 40 Exceptions | 4
10 | Schedulers/Listeners - Schedulers/Calendars | 0.077 | No scheduler/calendar | 0 | Removed
|  |  | Scheduler with Business Calendar | 1
|  |  | Scheduler based on Custom Events | 2
|  |  | Complex Scheduling | 3
11 | Target Application UI access mode | 0.077 | Direct Access | 0
|  |  | Citrix/Remote Desktop/VDI Access | 4
12 | Automation Scripting - No. of Scripts need to be build | 0.077 | No Scripts | 0 | Every 6 Automation Scripting - No. of Scripts need to be build, 1 story point to be added
|  |  | Up to 6 | 1
|  |  | 7 to 12 | 2
|  |  | 13 to 24 | 3
|  |  | 25 & above | 4
13 | Reusable Modules | 0.077 | No Reusable Module | 0 | Every 2 Reusable Modules need to be build, 1 story point to be added
|  |  | 1 to 2 | 1
|  |  | 3 to 4 | 2
14 | API Interfaces - No of Interface in user story | 0.077 | No API Interfaces | 0 | Every 3 API Interfaces - No of Interface in user story, 1 story point to be added
|  |  | 1 to 3 | 1
|  |  | 4 to 6 | 2
|  |  | 7 to 9 | 3
|  |  | 10 to 12 | 4
15 | Understanding existing automation (atmx) E2E (Enh. only) | 0.077 | No atmx file | 0
|  |  | 0 to 1500 Lines of Code | 1
|  |  | 1501 to 3000 Lines of Code | 2
|  |  | 3001 to 4500 Lines of Code | 4
16 | Understanding existing Macro/Other Scripts E2E (Enh. only) | 0.077 | No Macro/Other Scripts | 0
|  |  | 0 to 150 Lines of Scripts | 1
|  |  | 151 to 300 Lines of Scripts | 2
|  |  | 301 to 450 Lines of Scripts | 4
17 | Environment Readiness for Dev/QA/Prod | 0.077 | NA | 0 | 1. Coordination with Admin for Software Installation 2. Co-ordination with Admin for Configuration (try & catch) 3. Perform Smoke Test in Dev/QA 4. Prepare document and co-ordinate with Middleware Team for smoke test in prod
|  |  | Environment Readiness for Dev/QA/Prod | 1
18 | Solution Design (SDD) | 0.077 | NA | 0
|  |  | Standalone Architecture | 1
|  |  | Multi Bot Architecture without interaction with each other | 2
|  |  | Multi Bot Controller Architecture | 3
19 | Test Case Document & QAT |  | NA | 0 | Every 20 test cases 1 story point to be added
|  |  | Test Case up to 20 | 1
|  |  | Test Case from 21 to 40 | 2
|  |  | Test Case from 41 to 60 | 3
|  |  | Test Case from 61 to 80 | 4