## Sheet1 (2)
| Open Pointers | Purpose | Current Status | Nitin's Comment (If Any)
1 | Access to CLEAS Application | 1. To extract opportunity data for tracking the progress of new opportunities 2. To extract Engagement Letters/contracts | Call to be scheduled with Elaine koong
2 | Access to HANA application/Launchpad | To extract Engagement data | Reached out to Jonathan Gerber, he told me to reach out to Nitin for raising access for HANA. Currently, business team is using Launchpad to download the reports but launchpad is decommisioning soon, next steps are required to be clarified with business team
2.1 | Can we extract data for all the partners with one bot id from HANA or do we need multiple ids or Super admin access |  | Schedule call with business team Super admin access clarity required - not sure to whom I should reach out --??
3 | Access to Engage | To extract opportunity data only, however Holly and Stephanie are working to get this data on CLEAS | Required exceptional approval from FOT team. POC - mollywalter@KPMG.com
| Process related open points | Possible solutions | Action point
4 | Clarity required over how we will get the list of Partners for whom bot needs to download reports from HANA | Can we upload a excel file and put it on a Shared folder - This might be a live document This will create dependency on BETs to maintain the list | Will schedule call with business team. Please confirm shall I include Anna Garett in this call as well
5 | Clarity required over how we will get the list of new opportunity id's. What is the source ? Current source is email but due to unstructured format and all, unable to proceed with that | Can we upload a excel file and put it on a Shared folder - This might be a live document This will create dependency on BETs to maintain the list
6 | Clarity over how we can get the list of EAs so that tasks can be assigned to them from Power App dashboard | Can we upload a excel file and put it on a Shared folder - This might be a live document This will create dependency on BETs to maintain the list
7 | 1. Clarity required over from where we need to extract Engagement letters/contracts from CLEAS application. Whether we can download the contracts or not? 2. How bot would be able to identify which engagements needs to be updated? | Can we upload the contracts on a SharePoint ? This will create dependency on BETs to maintain theSharePoint folder